# AI DBA Copilot Platform - Comprehensive Project Plan

Project Duration: 22 Weeks
Project Sponsor: DBA / AI Automation Team
Objective: Build an AI-powered DBA platform that leverages MCP-based database telemetry, historical memory, AI-driven root cause analysis, Jira integration, and predictive analytics.

## Executive Summary

Create a centralized AI DBA platform for PostgreSQL, Oracle, RDS MySQL, and Databricks.

Leverage the existing MCP server as the telemetry and tool layer.

Build a PostgreSQL-based memory repository for incidents, recommendations, metrics, and outcomes.

Provide AI-assisted root cause analysis, recommendation generation, and Jira deduplication.

Enable future predictive analytics and automated remediation.

## Phase 1 – Platform Foundation (Weeks 1-2)

Establish repository database schemas.

Define incident, recommendation, Jira mapping, and metrics models.

Set up source control, CI/CD, Docker, and deployment standards.

Deliverable: Operational repository database and baseline architecture.

## Phase 2 – Memory Layer (Weeks 2-4)

Implement metric_snapshots, incidents, recommendations, remediation_history, and jira_mapping tables.

Define retention policies and partitioning strategy.

Deliverable: Historical knowledge repository with documented schema.

## Phase 3 – Issue Detection Engine (Weeks 4-6)

Consume MCP metrics and identify performance, capacity, availability, and maintenance issues.

Implement deterministic rules and severity scoring.

Deliverable: Automated issue detection service.

## Phase 4 – Jira Integration & Deduplication (Weeks 6-8)

Generate issue fingerprints.

Prevent duplicate Jira tickets.

Track ticket lifecycle and incident correlations.

Deliverable: Production-ready Jira synchronization service.

## Phase 5 – AI Recommendation Engine (Weeks 8-10)

Generate RCA reports.

Recommend tuning actions and remediation steps.

Provide confidence scoring and risk classification.

Deliverable: AI recommendation service with structured outputs.

## Phase 6 – MCP Tool Expansion (Weeks 10-12)

Standardize MCP tools for performance, configuration, capacity, and incident history.

Expose recommendation and incident search tools.

Deliverable: Unified MCP interface for AI agents.

## Phase 7 – Conversational DBA Copilot (Weeks 12-14)

Implement chat interface.

Support natural-language operational investigations.

Provide contextual recommendations using memory layer data.

Deliverable: AI DBA Copilot MVP.

## Phase 8 – Semantic Knowledge Base (Weeks 14-16)

Implement vector search using pgvector.

Support similar incident retrieval and historical RCA lookup.

Deliverable: Semantic incident search capability.

## Phase 9 – Predictive Analytics (Weeks 16-18)

Forecast storage exhaustion, replication issues, and connection saturation.

Generate proactive alerts.

Deliverable: Predictive monitoring module.

## Phase 10 – Automated Remediation (Weeks 18-22)

Automate low-risk actions.

Require approval workflows for medium/high-risk actions.

Implement audit logging and rollback tracking.

Deliverable: Controlled remediation framework.

## Success Metrics

Reduce duplicate Jira tickets by >95%.

Reduce DBA triage time by 50%.

Provide RCA generation within 5 minutes of incident detection.

Maintain complete incident and recommendation history.

Enable proactive identification of capacity and performance risks.